## Read Me
Kopano Community Hospital — ISO/IEC 27001:2022 Gap Assessment
FICTIONAL ORGANISATION — this document is part of a fictional hospital GRC portfolio project
and is not an assessment of any real facility.
Scope: The Information Security Management System (ISMS) scope for this assessment is the
clinical information environment at Kopano Community Hospital — the EHR, LIS, PACS, pharmacy
dispensing system, the biomedical device network, and supporting IT infrastructure.
Methodology: Each control in ISO/IEC 27001:2022 Annex A is assessed against current-state
evidence and rated Implemented, Partially Implemented, or Not Implemented, with a priority
and target date assigned to any gap. This is a representative subset of Annex A controls
selected for portfolio purposes, grouped under the four 2022 themes (Organisational, People,
Physical, Technological).
Status colour key: Green = Implemented, Amber = Partially Implemented, Red = Not Implemented.
Cross-references: Gaps identified here map to risks in 02_Risk_Register.xlsx via the
'Related Control' column, and to procedures in 05_Incident_Response_Playbook.docx and
06_Business_Continuity_DR_Summary.docx where relevant.

## Gap Assessment
Clause | Theme | Control | Current State Evidence | Status | Gap / Action Required | Priority | Owner | Target Date
A.5.1 | Organisational | Policies for information security | Draft Information Security Policy exists, approved by IT Manager only. | Partially Implemented | Obtain formal Hospital Board / CEO sign-off; schedule annual policy review cycle. | High | CIO | 2026-10-31
A.5.9 | Organisational | Inventory of information and other associated assets | Server and workstation asset register maintained in spreadsheet; biomedical devices tracked separately by Biomedical Engineering with inconsistent detail. | Partially Implemented | Consolidate IT and biomedical asset registers into a single CMDB; include firmware/OS version per device. | High | IT Manager | 2026-11-30
A.5.15 | Organisational | Access control | Role-based access control (RBAC) implemented on the EHR with ward-level restrictions; access reviews are ad hoc rather than scheduled. | Partially Implemented | Implement quarterly formal access recertification signed off by ward managers. | High | Information Officer | 2026-10-15
A.5.19 | Organisational | Information security in supplier relationships | LIS integration vendor contract has an SLA but no security schedule or breach notification clause. | Not Implemented | Add security and breach-notification clauses at next contract renewal; request current vendor security certification. | Medium | Head of Laboratory Services | 2027-02-28
A.5.24 | Organisational | Information security incident management planning | Incident Response Playbook drafted covering ransomware and medical device compromise scenarios; not yet tested via tabletop exercise. | Partially Implemented | Run a tabletop exercise with IT, Clinical Governance, and Communications; update playbook based on findings. | High | IT Manager | 2026-09-30
A.5.29 | Organisational | Information security during disruption | Downtime procedures documented for nursing stations; generator and UPS in place for critical systems. | Partially Implemented | Extend server-room UPS runtime; conduct an annual full-facility failover drill. | High | Facilities Manager | 2026-12-15
A.5.34 | Organisational | Privacy and protection of PII | POPIA Compliance Assessment completed identifying gaps in breach notification and retention/disposal for paper records. | Partially Implemented | Close out actions in POPIA Compliance Assessment Sections 5 and 7. | High | Information Officer | 2026-11-30
A.6.3 | People | Information security awareness, education and training | Annual POPIA awareness training delivered to clinical staff; no dedicated phishing simulation programme. | Partially Implemented | Introduce quarterly phishing simulations with follow-up micro-training for staff who click. | Medium | HR Manager / IT Manager | 2027-01-31
A.6.6 | People | Confidentiality or non-disclosure agreements | Confidentiality undertakings signed at onboarding; no periodic re-signing. | Partially Implemented | Introduce mandatory annual re-signing tied to performance review cycle. | Low | HR Manager | 2027-03-31
A.7.2 | Physical | Physical entry | Server room badge access with logging; general ward areas have reception-controlled entry only. | Partially Implemented | Extend badge-access logging review to monthly; add dual-authorisation for server room after-hours entry. | Medium | Facilities Manager | 2027-01-31
A.7.4 | Physical | Physical security monitoring | CCTV covers server room entrance and main hospital entrances; ward corridors have partial coverage. | Partially Implemented | Extend CCTV coverage to biomedical device storage areas; retain footage for 90 days minimum. | Low | Facilities Manager | 2027-04-30
A.8.1 | Technological | User endpoint devices | Screen auto-lock (5 min) enforced via group policy on clinical workstations. | Implemented | Reduce timeout to 2 minutes on shared nursing-station terminals. | Low | IT Manager | 2027-02-28
A.8.3 | Technological | Information access restriction | EHR access restricted by role and ward; audit logging enabled but not routinely reviewed. | Partially Implemented | Implement automated alerting for anomalous access patterns (bulk exports, VIP records). | High | Information Officer | 2026-10-31
A.8.8 | Technological | Management of technical vulnerabilities | No formal vulnerability scanning programme for clinical network; ad hoc patching. | Not Implemented | Stand up a quarterly vulnerability scanning programme for clinical and biomedical VLANs, with a documented patching SLA. | High | IT Manager | 2026-09-30
A.8.9 | Technological | Configuration management | No documented secure baseline configuration for clinical workstations or medical devices. | Not Implemented | Define and apply secure baseline configurations; document deviations for legacy medical devices with compensating controls. | High | IT Manager / Biomedical Engineering Lead | 2026-12-31
A.8.13 | Technological | Information backup | Nightly backups of EHR database; offline copy exists but not fully air-gapped or immutable. | Partially Implemented | Implement an immutable, air-gapped backup copy and test full restoration quarterly. | High | IT Manager | 2026-10-31
A.8.16 | Technological | Monitoring activities | No centralised security monitoring (SIEM) across clinical and corporate networks. | Not Implemented | Evaluate a managed SIEM/SOC service appropriate to a public-hospital budget; prioritise clinical network coverage first. | Medium | CIO | 2027-06-30
A.8.20 | Technological | Networks security | Clinical network segmented from corporate network; biomedical devices on a dedicated VLAN with firewall rules. | Implemented | Review firewall rule set annually; document rule justifications. | Medium | IT Manager | 2027-03-31
A.8.22 | Technological | Segregation of networks | Biomedical VLAN isolated from general clinical VLAN; some legacy devices found bridged during last informal review. | Partially Implemented | Complete a full network audit to identify and remediate any bridged/misconfigured devices. | High | IT Manager | 2026-09-30
A.8.24 | Technological | Use of cryptography | Database-level encryption enabled for EHR at rest; encryption in transit inconsistent across legacy interfaces (e.g. older LIS connections). | Partially Implemented | Enforce TLS on all clinical system interfaces; retire or isolate interfaces that cannot support it. | Medium | IT Manager | 2027-02-28
A.8.32 | Technological | Change management | Change advisory board (CAB) covers major EHR/PACS changes; minor/urgent patches applied outside the process. | Partially Implemented | Extend CAB scope to all clinical-system changes, including emergency patches, with a documented rollback plan requirement. | Medium | IT Manager | 2027-01-31

## Summary
Gap Assessment Summary
Status | Count
Implemented | 2
Partially Implemented | 15
Not Implemented | 4
Total controls assessed | 21